## Roadmap
Title | Start Date | End Date | Category | Description | Status | Owner | Label
Brand Refresh & Guidelines | 2025-01-06 | 2025-02-14 | Marketing | Update brand identity, logo, and style guide | done | Sarah | M1
Website Redesign | 2025-01-20 | 2025-03-31 | Marketing | Complete redesign of company website | in_progress | Sarah | M2
Product Launch Campaign | 2025-03-01 | 2025-05-15 | Marketing | Multi-channel launch campaign | planned | Tom | M3
Customer Testimonials | 2025-04-01 | 2025-05-01 | Marketing | Gather and produce 10 video testimonials | planned | Sarah | M4
Trade Show Preparation | 2025-05-01 | 2025-06-15 | Marketing | Booth design, materials, demos | planned | Tom | M5
Customer Research Interviews | 2025-01-06 | 2025-02-07 | Product | Interview 30 customers on pain points | done | Lisa | P1
Product Requirements Document | 2025-02-01 | 2025-02-28 | Product | Define MVP features and specs | done | Lisa | P2
UX/UI Design & Prototypes | 2025-02-15 | 2025-04-15 | Product | Design screens and clickable prototype | in_progress | Amy | P3
Beta Testing Program | 2025-04-15 | 2025-06-01 | Product | Recruit 50 beta testers, gather feedback | planned | Lisa | P4
Product Documentation | 2025-05-01 | 2025-06-15 | Product | User guides, help center articles | planned | Amy | P5
Core Platform Build | 2025-02-15 | 2025-05-31 | Engineering | Build backend services and database | in_progress | Mike | E1
Mobile App Development | 2025-03-15 | 2025-06-15 | Engineering | iOS and Android app development | planned | Dave | E2
Payment Integration | 2025-03-01 | 2025-04-30 | Engineering | Stripe and PayPal integration | in_progress | Mike | E3
Performance & Load Testing | 2025-05-15 | 2025-06-15 | Engineering | Ensure system handles 10K users | planned | Dave | E4
Security Audit & Fixes | 2025-06-01 | 2025-06-30 | Engineering | Third-party security assessment | planned | Mike | E5
Vendor Selection | 2025-01-06 | 2025-01-31 | Operations | Evaluate and select key vendors | done | Karen | O1
Hiring Plan Execution | 2025-01-13 | 2025-04-30 | Operations | Hire 8 new team members | in_progress | Karen | O2
Office Expansion Setup | 2025-03-01 | 2025-04-15 | Operations | New floor buildout and move | planned | Karen | O3
Partner Onboarding | 2025-04-01 | 2025-05-31 | Operations | Onboard 5 channel partners | planned | Rob | O4
Launch Readiness Review | 2025-06-01 | 2025-06-30 | Operations | Final go/no-go checklist | planned | Karen | O5
Sales Playbook Creation | 2025-02-01 | 2025-03-15 | Sales | Build pitch decks, battle cards, scripts | in_progress | Jake | S1
Sales Team Training | 2025-03-15 | 2025-04-15 | Sales | Product training for 12 reps | planned | Jake | S2
Pilot Customer Program | 2025-04-15 | 2025-06-30 | Sales | Sign 5 pilot customers | planned | Nina | S3
CRM & Pipeline Setup | 2025-01-20 | 2025-02-28 | Sales | Configure Salesforce for new product | done | Nina | S4
Pricing Strategy | 2025-02-15 | 2025-03-15 | Sales | Finalize pricing tiers and packages | in_progress | Jake | S5

## Instructions
Roadmap Pro — Input Guide
Required Columns:
Title | Name of the work item (e.g., 'API Gateway Development')
Start Date | When work begins (YYYY-MM-DD format)
End Date | When work ends (YYYY-MM-DD format)
Optional Columns:
Category | Team or workstream (e.g., Platform, Product, Security)
Description | Brief description of the work
Status | planned, in_progress, done, or at_risk
Owner | Person responsible
Label | Short label (e.g., D1, MVP, Phase 2)
Tips:
• Categories are used to color-code items and group them in swim lanes
• For milestones, set Start Date = End Date
• The app auto-detects date ranges — no settings sheet needed
• Column names are flexible: 'Name' works for 'Title', 'Team' for 'Category', etc.