## Settings
key | value
chart_title | Sep 2025 Roadmap (Subject to Change)
chart_subtitle | Blocked diagram / swimlane Gantt example
confidentiality_label | Dayforce Confidential
overall_start_date | 2025-09-15
overall_end_date | 2026-02-15
timezone | America/Chicago
week_start_day | Mon
time_granularity | Weekly
output_dpi | 300
show_today_line | TRUE
today_line_date
page_size | A3
font_family | Calibri

## Workstreams
workstream | order | color
Release | 1 | Blue
Legal | 2 | Orange
Product | 3 | Green
Marketing | 4 | Purple
Integration | 5 | Red
GTM | 6 | Cyan
Project TEST | 7 | Gray

## Tasks
id | workstream | title | description | start_date | end_date | status | owner | color_override | type | hyperlink
L-001 | Legal | Target Close | Deal target close milestone | 2025-10-01 | 2025-10-01 | planned | Legal |  | milestone | https://example.com
P-001 | Product | Tech Diligence Deep Dive | Deep dive with founders | 2025-09-18 | 2025-09-18 | done | Product |  | milestone
P-002 | Product | Cloud & Data Diligence Review |  | 2025-09-26 | 2025-09-26 | done | Product |  | milestone
P-003 | Product | Integration Plan Draft | Design initial integration approach; capture constraints | 2025-09-20 | 2025-10-20 | in_progress | Product |  | block
R-001 | Release | SWP 1.0 Planning | Design and timeline the initial iFrame integration plan | 2025-10-01 | 2025-12-15 | in_progress | Release |  | block
R-002 | Release | SWP 1.0 Release | SSO + UX integration + API data access | 2026-01-01 | 2026-01-01 | planned | Release |  | milestone
R-003 | Release | SWP 2.0 Planning | Define data + AI objectives and timeline | 2026-01-15 | 2026-02-15 | planned | Release |  | block
M-001 | Marketing | Press Release Draft | Draft complete and distributed for review | 2025-09-29 | 2025-10-01 | done | Marketing |  | block
M-002 | Marketing | Comms Plan Build-out | Finalize messaging + distribution plan | 2025-09-29 | 2025-10-07 | in_progress | Marketing |  | block
M-003 | Marketing | Discover Activities | Mainstage + spotlights + analyst day + booth | 2025-10-07 | 2025-10-09 | planned | Marketing |  | block
M-004 | Marketing | Press Release Launch Assets | Webpage + social + customer/partner comms | 2025-10-07 | 2025-10-10 | planned | Marketing |  | block
M-005 | Marketing | Webinar 1 | Marketing webinar placeholder | 2025-11-18 | 2025-11-18 | planned | Marketing |  | milestone
M-006 | Marketing | Webinar 2 | Marketing webinar placeholder | 2025-12-09 | 2025-12-09 | planned | Marketing |  | milestone
G-001 | GTM | Financial Model Review | Review model with stakeholders | 2025-09-16 | 2025-09-16 | done | GTM |  | milestone
G-002 | GTM | Offering Strategy Confirmed |  | 2025-09-29 | 2025-09-29 | done | GTM |  | milestone
G-003 | GTM | Pricing & Packaging Build | Build complete + contract requirements | 2025-10-06 | 2025-10-06 | in_progress | GTM |  | milestone
G-004 | GTM | SFDC & QTO Systems Release | Salesforce off-cycle release (tentative) | 2025-11-21 | 2025-11-21 | planned | GTM |  | milestone
I-001 | Integration | Demo Instance Established | Standalone data set in demo environment | 2025-09-26 | 2025-09-26 | done | Integration |  | milestone
I-002 | Integration | Demo Prep | Branding + dataset finalized; demo script | 2025-10-03 | 2025-10-03 | done | Integration |  | milestone
T-001 | Project TEST | Parallel Workstream Test A | Overlaps with Test B to demonstrate stacking | 2025-10-01 | 2025-10-20 | planned | PMO |  | block
T-002 | Project TEST | Parallel Workstream Test B | Overlaps with Test A | 2025-10-10 | 2025-10-25 | planned | PMO |  | block
T-003 | Project TEST | Parallel Workstream Test C | Fits after A ends | 2025-10-21 | 2025-11-05 | planned | PMO |  | block